## Sheet3
Pending
On Schedule
Delayed
Critical
Completed

## Sheet1
Extraterrestrial Robot Explorer and Environmental Logger
Kevin Hartwig, James Sonnenberg and Ovi Ofrim
PROJECT SCHEDULE
Last updated: October 13, 2016
Week Ending | Phase | Primary Task |  | Subtasks | Assigned | Status
2016-10-07 | Planning | A | Finalize Specification for proof of concept | 1. Clarify the contents/scope of this specification. What does this specific specification require? (i.e., Audience, purpose, level of detail, technical vs functional) | All | On Schedule
|  |  |  | 2. Complete the specification. | All | On Schedule
|  |  |  | 3. Submit to group members for final revisions and editing. | All | On Schedule
|  | B | Finalize selection of sensors and start technical reports on assigned sensors | Pending… | All | On Schedule
|  | C | Familiarize group with Raspberry Pi development environment | 1. Boot up the Raspberry Pi and spend an hour exploring the environment. | Ovi | Completed
|  |  |  | 2. Write some test code. Something that may be useful to the project eventually would be nice (ex., USB or Wi-Fi device initialization) | Ovi | Completed
|  |  |  | 3. Give a tour of the OS to the other group members. Explain the example code functionality. | Ovi | Completed
|  | D | Get encoders working | 1. Resurrect required resources from last semester and create a new project for testing the encoder software independently of the project. | All | Completed
|  |  |  | 2. Write code that counts encoder veins while the wheels are spinning | All | Completed
|  |  |  | 3. Write code that uses the counted encoder veins to determine speed and position of robot | All | Critical
|  |  |  | 4. Integrate the independently validated encoder control software with the project code. | All | Critical
|  |  |  | 5. Test that functionality of the encoders is still correct and that no other functionality has been impaired by the integration. | All | Critical
|  | E | Choose the Supervisory control method | 1. Experiment with the console in the Linux environment. Create code to gauge the level of complexity of tracking of keystrokes, including keys held and released, and any associated delays. | Kevin | Completed
|  |  |  | 2. Create a list of pros/cons for each of the methods available (Joystick, Scripts or Keyboard). | Kevin | Completed
|  |  |  | 3. Present findings to the group and make a final decision on the control method. | Kevin | Completed
|  | F | Finish COTS selection matrix | 1. Gather power requirements of the Linux box (i.e., must power the camera, etc) | James | Completed
|  |  |  | 2. Finalize document, including any last requirements (power requirements from above) and associated analysis of possible solutions. | James | Completed
|  |  |  | 3. Present findings to the group and purchase/secure the selected COTS Linux box. | James | Completed
2016-10-14 | Design | A | Get PID control working on the robot platform | 1. Ensure encoders working with engineering units | All | Delayed
|  |  |  | 2. Determine method of importing PID control into the system (writing code manually, using SimuLink) | All | Delayed
|  |  |  | 3. Test and adjust PID control on the robot in an individual project. | All | Delayed
|  |  |  | 4. Integrate with the main project code. | All | Delayed
|  | B | Prepare Raspberry Pi for Wi-Fi connection | 1. Get Raspbian OS onto the raspberry Pi | Ovi | Completed
|  |  |  | 2. Install Eclipse and C/C++ extension | Ovi | Completed
|  |  |  | 3. Start working on communications between Pi and Laptop over Wi-Fi link | Ovi | Completed
|  | C | Begin adjusting supervisory Linux program to work with the selected control method (i.e., Joystick…) | 1. Prepare a new communication protocol based on the selected control method. | Kevin | Completed
|  |  |  | 2. Implement the new communication protocol into the existing program. | Kevin | Completed
|  | D | Initialize RS-232 on the Pi and get communication between it and the platform controller working. | 1. Identify the name of the device (i.e. /dev/tty___), using the USB-DB9 converter. | James | Completed
|  |  |  | 2. Decide on one of two options: (a) write a new program to communicate with the port, or (b) try to recycle the Linux Supervisor port communication code to work on the Pi. | James | Completed
|  |  |  | 3. (a) Simulate communication using real term. (b) Communicate between the Pi and the Axman. | James | Delayed
|  |  |  | 4. Integrate with the platform controller: ensure reliable communications between the modules. | James | Delayed
|  | E | Investigate the need for threading in the supervisory Linux program | 1. Create a pros/cons list of threading vs single thread program. Is the response of the system significantly affected if we only use a single thread? | Kevin | Completed
|  |  |  | 2. If threading is deemed favourable or necessary, begin implementing threading. Ask Peter for a re-cap (or go back to old notes) on the common pitfalls and mistakes made when threading they can be avoided. | Kevin | Completed
2016-10-21 | Design | A | Establish a reliable communication link between the Supervisory control program and the Raspberry Pi over Wi-Fi. | 1. Raspberry Pi running Raspbian |  | Pending
|  |  |  | 2. Load test code onto the pi using the micro SD card |  | Pending
|  |  |  | 3. Connect host computer to local area network via router provided by Peter + Bill |  | Pending
|  |  |  | 4. Using socket communication send and echo back a single char |  | Pending
|  |  |  | 5. Send and echo back strings |  | Pending
|  | B | Finalize code for the selected control method in the supervisory control program. Implement threading if you have chosen to do so. | 1. Integrate Encoders into project supervisor |  | Pending
|  |  |  | 2. Integrate PID control |  | Pending
|  |  |  | 3. Intergrate Joystick/ArrowKey control …… Create thread |  | Pending
|  |  |  | 4. Test and verify functionality |  | Pending
|  | C | Integrate any environmental sensors onto the board, if you have decided to do so for bonus marks. | 1. Pick desired sensors to add |  | Pending
|  |  |  | 2. Create protoboard/PCB for signal conditioning circuit |  | Pending
|  |  |  | 3. Mount enironmental sensors to the robot |  | Pending
|  |  |  | 4. Test and verify functionality of sensors |  | Pending
2016-10-28 | Final Integration and Testing | A | Integrate the major system modules: Supervisor, Linux Box, and Platform Controller. Establish and confirm reliable communication between all modules. |  |  | Pending
|  | B | Write code to incorporate any environmental sensor functionality in both the Supervisor and the Platform, if any are mounted to the board. |  |  | Pending
2016-11-04 | Final Integration and Testing | A | Verify and validate complete system functionality. |  |  | Pending
|  | B | Complete any missed or overdue tasks. |  |  | Pending